## Timeline
Board - Roadmap (by weeks)
|  |  | Oct-2023 | Oct-2023 | Oct-2023 | Oct-2023 | Oct-2023 | Oct-2023 | Oct-2023 | Oct-2023 | Oct-2023 | Oct-2023 | Oct-2023 | Oct-2023 | Oct-2023 | Oct-2023 | Oct-2023 | Oct-2023 | Nov-2023 | Nov-2023 | Nov-2023 | Nov-2023 | Nov-2023 | Nov-2023 | Nov-2023 | Nov-2023 | Nov-2023 | Nov-2023 | Nov-2023 | Nov-2023 | Nov-2023 | Nov-2023 | Nov-2023 | Nov-2023 | Nov-2023 | Nov-2023 | Nov-2023 | Nov-2023 | Nov-2023 | Nov-2023 | Nov-2023 | Nov-2023 | Nov-2023 | Nov-2023 | Nov-2023 | Nov-2023 | Nov-2023 | Nov-2023 | Dec-2023 | Dec-2023 | Dec-2023 | Dec-2023 | Dec-2023 | Dec-2023 | Dec-2023 | Dec-2023 | Dec-2023 | Dec-2023 | Dec-2023 | Dec-2023 | Dec-2023 | Dec-2023 | Dec-2023 | Dec-2023 | Dec-2023 | Dec-2023 | Dec-2023 | Dec-2023 | Dec-2023 | Dec-2023 | Dec-2023 | Dec-2023 | Dec-2023 | Dec-2023 | Dec-2023 | Dec-2023 | Dec-2023 | Dec-2023
| Start | End | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Initiation - Weeks 1 & 2 - Project Planning |  |  | 16: Initiation - Weeks 1 & 2 - Project Planning
Assign roles and responsibilities to each team member | 16-Oct-2023 | 23-Oct-2023 | 16: Assign roles and responsibilities to each team member (16-Oct-23 - 23-Oct-23); 17: Assign roles and responsibilities to each team member (16-Oct-23 - 23-Oct-23); 18: Assign roles and responsibilities to each team member (16-Oct-23 - 23-Oct-23); 19: Assign roles and responsibilities to each team member (16-Oct-23 - 23-Oct-23); 20: Assign roles and responsibilities to each team member (16-Oct-23 - 23-Oct-23); 21: Assign roles and responsibilities to each team member (16-Oct-23 - 23-Oct-23); 22: Assign roles and responsibilities to each team member (16-Oct-23 - 23-Oct-23); 23: Assign roles and responsibilities to each team member (16-Oct-23 - 23-Oct-23)
Define communication channels and tools for collaboration | 16-Oct-2023 | 23-Oct-2023 | 16: Define communication channels and tools for collaboration (16-Oct-23 - 23-Oct-23); 17: Define communication channels and tools for collaboration (16-Oct-23 - 23-Oct-23); 18: Define communication channels and tools for collaboration (16-Oct-23 - 23-Oct-23); 19: Define communication channels and tools for collaboration (16-Oct-23 - 23-Oct-23); 20: Define communication channels and tools for collaboration (16-Oct-23 - 23-Oct-23); 21: Define communication channels and tools for collaboration (16-Oct-23 - 23-Oct-23); 22: Define communication channels and tools for collaboration (16-Oct-23 - 23-Oct-23); 23: Define communication channels and tools for collaboration (16-Oct-23 - 23-Oct-23)
Feasability Study - Considerations | 16-Oct-2023 | 23-Oct-2023 | 16: Feasability Study - Considerations (16-Oct-23 - 23-Oct-23); 17: Feasability Study - Considerations (16-Oct-23 - 23-Oct-23); 18: Feasability Study - Considerations (16-Oct-23 - 23-Oct-23); 19: Feasability Study - Considerations (16-Oct-23 - 23-Oct-23); 20: Feasability Study - Considerations (16-Oct-23 - 23-Oct-23); 21: Feasability Study - Considerations (16-Oct-23 - 23-Oct-23); 22: Feasability Study - Considerations (16-Oct-23 - 23-Oct-23); 23: Feasability Study - Considerations (16-Oct-23 - 23-Oct-23)
Deciding on Methods for Research and Analysis | 19-Oct-2023 | 23-Oct-2023 | 19: Deciding on Methods for Research and Analysis (19-Oct-23 - 23-Oct-23); 20: Deciding on Methods for Research and Analysis (19-Oct-23 - 23-Oct-23); 21: Deciding on Methods for Research and Analysis (19-Oct-23 - 23-Oct-23); 22: Deciding on Methods for Research and Analysis (19-Oct-23 - 23-Oct-23); 23: Deciding on Methods for Research and Analysis (19-Oct-23 - 23-Oct-23)
Deciding on Pre-processing approach | 19-Oct-2023 | 27-Oct-2023 | 19: Deciding on Pre-processing approach (19-Oct-23 - 27-Oct-23); 20: Deciding on Pre-processing approach (19-Oct-23 - 27-Oct-23); 21: Deciding on Pre-processing approach (19-Oct-23 - 27-Oct-23); 22: Deciding on Pre-processing approach (19-Oct-23 - 27-Oct-23); 23: Deciding on Pre-processing approach (19-Oct-23 - 27-Oct-23); 24: Deciding on Pre-processing approach (19-Oct-23 - 27-Oct-23); 25: Deciding on Pre-processing approach (19-Oct-23 - 27-Oct-23); 26: Deciding on Pre-processing approach (19-Oct-23 - 27-Oct-23); 27: Deciding on Pre-processing approach (19-Oct-23 - 27-Oct-23)
Decide predictors, variables (pdf - unemployment, inflation and real inflation) | 19-Oct-2023 | 27-Oct-2023 | 19: Decide predictors, variables (pdf - unemployment, inflation and real inflation) (19-Oct-23 - 27-Oct-23); 20: Decide predictors, variables (pdf - unemployment, inflation and real inflation) (19-Oct-23 - 27-Oct-23); 21: Decide predictors, variables (pdf - unemployment, inflation and real inflation) (19-Oct-23 - 27-Oct-23); 22: Decide predictors, variables (pdf - unemployment, inflation and real inflation) (19-Oct-23 - 27-Oct-23); 23: Decide predictors, variables (pdf - unemployment, inflation and real inflation) (19-Oct-23 - 27-Oct-23); 24: Decide predictors, variables (pdf - unemployment, inflation and real inflation) (19-Oct-23 - 27-Oct-23); 25: Decide predictors, variables (pdf - unemployment, inflation and real inflation) (19-Oct-23 - 27-Oct-23); 26: Decide predictors, variables (pdf - unemployment, inflation and real inflation) (19-Oct-23 - 27-Oct-23); 27: Decide predictors, variables (pdf - unemployment, inflation and real inflation) (19-Oct-23 - 27-Oct-23)
Can we answer all the questions in the brief | 19-Oct-2023 | 27-Oct-2023 | 19: Can we answer all the questions in the brief (19-Oct-23 - 27-Oct-23); 20: Can we answer all the questions in the brief (19-Oct-23 - 27-Oct-23); 21: Can we answer all the questions in the brief (19-Oct-23 - 27-Oct-23); 22: Can we answer all the questions in the brief (19-Oct-23 - 27-Oct-23); 23: Can we answer all the questions in the brief (19-Oct-23 - 27-Oct-23); 24: Can we answer all the questions in the brief (19-Oct-23 - 27-Oct-23); 25: Can we answer all the questions in the brief (19-Oct-23 - 27-Oct-23); 26: Can we answer all the questions in the brief (19-Oct-23 - 27-Oct-23); 27: Can we answer all the questions in the brief (19-Oct-23 - 27-Oct-23)
Create a shared project timeline through the Project RoadMap | 21-Oct-2023 | 23-Oct-2023 | 21: Create a shared project timeline through the Project RoadMap (21-Oct-23 - 23-Oct-23); 22: Create a shared project timeline through the Project RoadMap (21-Oct-23 - 23-Oct-23); 23: Create a shared project timeline through the Project RoadMap (21-Oct-23 - 23-Oct-23)
Setting up our GitHub Repo | 21-Oct-2023 | 23-Oct-2023 | 21: Setting up our GitHub Repo (21-Oct-23 - 23-Oct-23); 22: Setting up our GitHub Repo (21-Oct-23 - 23-Oct-23); 23: Setting up our GitHub Repo (21-Oct-23 - 23-Oct-23)
Identify any Data Challenges | 21-Oct-2023 | 23-Oct-2023 | 21: Identify any Data Challenges (21-Oct-23 - 23-Oct-23); 22: Identify any Data Challenges (21-Oct-23 - 23-Oct-23); 23: Identify any Data Challenges (21-Oct-23 - 23-Oct-23)
Set project milestones and deadlines | 21-Oct-2023 | 23-Oct-2023 | 21: Set project milestones and deadlines (21-Oct-23 - 23-Oct-23); 22: Set project milestones and deadlines (21-Oct-23 - 23-Oct-23); 23: Set project milestones and deadlines (21-Oct-23 - 23-Oct-23)
Completing and Signing Group Charter | 23-Oct-2023 | 23-Oct-2023 | 23: Completing and Signing Group Charter (23-Oct-23 - 23-Oct-23)
Assignment 1: Project scope and plan - 15% |  |  | 16: Assignment 1: Project scope and plan - 15%
Background/context and clearly defined problem statement (200 words) | 23-Oct-2023 | 23-Oct-2023 | 23: Background/context and clearly defined problem statement (200 words) (23-Oct-23 - 23-Oct-23)
Team roles and ways of working (250 words) | 23-Oct-2023 | 23-Oct-2023 | 23: Team roles and ways of working (250 words) (23-Oct-23 - 23-Oct-23)
Project plan (350 words): | 23-Oct-2023 | 23-Oct-2023 | 23: Project plan (350 words): (23-Oct-23 - 23-Oct-23)
Analytical approach (200 words) | 23-Oct-2023 | 23-Oct-2023 | 23: Analytical approach (200 words) (23-Oct-23 - 23-Oct-23)
Create Road Map and show within Appendix | 23-Oct-2023 | 23-Oct-2023 | 23: Create Road Map and show within Appendix (23-Oct-23 - 23-Oct-23)
Phase 1 of Analysis - Planning - Data Collection, Preparation & Cleaning |  |  | 16: Phase 1 of Analysis - Planning - Data Collection, Preparation & Cleaning
Acquire the supplied data set of central bank speeches | 23-Oct-2023 | 30-Oct-2023 | 23: Acquire the supplied data set of central bank speeches (23-Oct-23 - 30-Oct-23); 24: Acquire the supplied data set of central bank speeches (23-Oct-23 - 30-Oct-23); 25: Acquire the supplied data set of central bank speeches (23-Oct-23 - 30-Oct-23); 26: Acquire the supplied data set of central bank speeches (23-Oct-23 - 30-Oct-23); 27: Acquire the supplied data set of central bank speeches (23-Oct-23 - 30-Oct-23); 28: Acquire the supplied data set of central bank speeches (23-Oct-23 - 30-Oct-23); 29: Acquire the supplied data set of central bank speeches (23-Oct-23 - 30-Oct-23); 30: Acquire the supplied data set of central bank speeches (23-Oct-23 - 30-Oct-23)
Utilise Python in Jupyter Notebook for data handling | 23-Oct-2023 | 30-Oct-2023 | 23: Utilise Python in Jupyter Notebook for data handling (23-Oct-23 - 30-Oct-23); 24: Utilise Python in Jupyter Notebook for data handling (23-Oct-23 - 30-Oct-23); 25: Utilise Python in Jupyter Notebook for data handling (23-Oct-23 - 30-Oct-23); 26: Utilise Python in Jupyter Notebook for data handling (23-Oct-23 - 30-Oct-23); 27: Utilise Python in Jupyter Notebook for data handling (23-Oct-23 - 30-Oct-23); 28: Utilise Python in Jupyter Notebook for data handling (23-Oct-23 - 30-Oct-23); 29: Utilise Python in Jupyter Notebook for data handling (23-Oct-23 - 30-Oct-23); 30: Utilise Python in Jupyter Notebook for data handling (23-Oct-23 - 30-Oct-23)
Compile all necessary data into a structured dataset in Python | 23-Oct-2023 | 30-Oct-2023 | 23: Compile all necessary data into a structured dataset in Python (23-Oct-23 - 30-Oct-23); 24: Compile all necessary data into a structured dataset in Python (23-Oct-23 - 30-Oct-23); 25: Compile all necessary data into a structured dataset in Python (23-Oct-23 - 30-Oct-23); 26: Compile all necessary data into a structured dataset in Python (23-Oct-23 - 30-Oct-23); 27: Compile all necessary data into a structured dataset in Python (23-Oct-23 - 30-Oct-23); 28: Compile all necessary data into a structured dataset in Python (23-Oct-23 - 30-Oct-23); 29: Compile all necessary data into a structured dataset in Python (23-Oct-23 - 30-Oct-23); 30: Compile all necessary data into a structured dataset in Python (23-Oct-23 - 30-Oct-23)
Import and cleaning of data, ready for Analysis | 23-Oct-2023 | 30-Oct-2023 | 23: Import and cleaning of data, ready for Analysis (23-Oct-23 - 30-Oct-23); 24: Import and cleaning of data, ready for Analysis (23-Oct-23 - 30-Oct-23); 25: Import and cleaning of data, ready for Analysis (23-Oct-23 - 30-Oct-23); 26: Import and cleaning of data, ready for Analysis (23-Oct-23 - 30-Oct-23); 27: Import and cleaning of data, ready for Analysis (23-Oct-23 - 30-Oct-23); 28: Import and cleaning of data, ready for Analysis (23-Oct-23 - 30-Oct-23); 29: Import and cleaning of data, ready for Analysis (23-Oct-23 - 30-Oct-23); 30: Import and cleaning of data, ready for Analysis (23-Oct-23 - 30-Oct-23)
Phase 2 of Analysis - Execution- Text Preprocessing. Sentiment, Correlation & Predtictive Analysis |  |  | 16: Phase 2 of Analysis - Execution- Text Preprocessing. Sentiment, Correlation & Predtictive Analysis
Text Preprocessing | 30-Oct-2023 | 06-Nov-2023 | 30: Text Preprocessing (30-Oct-23 - 06-Nov-23); 31: Text Preprocessing (30-Oct-23 - 06-Nov-23); 1: Text Preprocessing (30-Oct-23 - 06-Nov-23); 2: Text Preprocessing (30-Oct-23 - 06-Nov-23); 3: Text Preprocessing (30-Oct-23 - 06-Nov-23); 4: Text Preprocessing (30-Oct-23 - 06-Nov-23); 5: Text Preprocessing (30-Oct-23 - 06-Nov-23); 6: Text Preprocessing (30-Oct-23 - 06-Nov-23)
Refine speeches - Lemmatisation | 30-Oct-2023 | 06-Nov-2023 | 30: Refine speeches - Lemmatisation (30-Oct-23 - 06-Nov-23); 31: Refine speeches - Lemmatisation (30-Oct-23 - 06-Nov-23); 1: Refine speeches - Lemmatisation (30-Oct-23 - 06-Nov-23); 2: Refine speeches - Lemmatisation (30-Oct-23 - 06-Nov-23); 3: Refine speeches - Lemmatisation (30-Oct-23 - 06-Nov-23); 4: Refine speeches - Lemmatisation (30-Oct-23 - 06-Nov-23); 5: Refine speeches - Lemmatisation (30-Oct-23 - 06-Nov-23); 6: Refine speeches - Lemmatisation (30-Oct-23 - 06-Nov-23)
Tokenisation | 30-Oct-2023 | 06-Nov-2023 | 30: Tokenisation (30-Oct-23 - 06-Nov-23); 31: Tokenisation (30-Oct-23 - 06-Nov-23); 1: Tokenisation (30-Oct-23 - 06-Nov-23); 2: Tokenisation (30-Oct-23 - 06-Nov-23); 3: Tokenisation (30-Oct-23 - 06-Nov-23); 4: Tokenisation (30-Oct-23 - 06-Nov-23); 5: Tokenisation (30-Oct-23 - 06-Nov-23); 6: Tokenisation (30-Oct-23 - 06-Nov-23)
Sentiment extraction using NLP tools like NLTK and TextBlob | 30-Oct-2023 | 06-Nov-2023 | 30: Sentiment extraction using NLP tools like NLTK and TextBlob (30-Oct-23 - 06-Nov-23); 31: Sentiment extraction using NLP tools like NLTK and TextBlob (30-Oct-23 - 06-Nov-23); 1: Sentiment extraction using NLP tools like NLTK and TextBlob (30-Oct-23 - 06-Nov-23); 2: Sentiment extraction using NLP tools like NLTK and TextBlob (30-Oct-23 - 06-Nov-23); 3: Sentiment extraction using NLP tools like NLTK and TextBlob (30-Oct-23 - 06-Nov-23); 4: Sentiment extraction using NLP tools like NLTK and TextBlob (30-Oct-23 - 06-Nov-23); 5: Sentiment extraction using NLP tools like NLTK and TextBlob (30-Oct-23 - 06-Nov-23); 6: Sentiment extraction using NLP tools like NLTK and TextBlob (30-Oct-23 - 06-Nov-23)
Calculate overall sentiment score- for each text, presented as a percentage | 30-Oct-2023 | 06-Nov-2023 | 30: Calculate overall sentiment score- for each text, presented as a percentage (30-Oct-23 - 06-Nov-23); 31: Calculate overall sentiment score- for each text, presented as a percentage (30-Oct-23 - 06-Nov-23); 1: Calculate overall sentiment score- for each text, presented as a percentage (30-Oct-23 - 06-Nov-23); 2: Calculate overall sentiment score- for each text, presented as a percentage (30-Oct-23 - 06-Nov-23); 3: Calculate overall sentiment score- for each text, presented as a percentage (30-Oct-23 - 06-Nov-23); 4: Calculate overall sentiment score- for each text, presented as a percentage (30-Oct-23 - 06-Nov-23); 5: Calculate overall sentiment score- for each text, presented as a percentage (30-Oct-23 - 06-Nov-23); 6: Calculate overall sentiment score- for each text, presented as a percentage (30-Oct-23 - 06-Nov-23)
Conduct sentiment analysis on central bank speeches | 30-Oct-2023 | 06-Nov-2023 | 30: Conduct sentiment analysis on central bank speeches (30-Oct-23 - 06-Nov-23); 31: Conduct sentiment analysis on central bank speeches (30-Oct-23 - 06-Nov-23); 1: Conduct sentiment analysis on central bank speeches (30-Oct-23 - 06-Nov-23); 2: Conduct sentiment analysis on central bank speeches (30-Oct-23 - 06-Nov-23); 3: Conduct sentiment analysis on central bank speeches (30-Oct-23 - 06-Nov-23); 4: Conduct sentiment analysis on central bank speeches (30-Oct-23 - 06-Nov-23); 5: Conduct sentiment analysis on central bank speeches (30-Oct-23 - 06-Nov-23); 6: Conduct sentiment analysis on central bank speeches (30-Oct-23 - 06-Nov-23)
Analyse how sentiment has changed over time | 03-Nov-2023 | 09-Nov-2023 | 3: Analyse how sentiment has changed over time (03-Nov-23 - 09-Nov-23); 4: Analyse how sentiment has changed over time (03-Nov-23 - 09-Nov-23); 5: Analyse how sentiment has changed over time (03-Nov-23 - 09-Nov-23); 6: Analyse how sentiment has changed over time (03-Nov-23 - 09-Nov-23); 7: Analyse how sentiment has changed over time (03-Nov-23 - 09-Nov-23); 8: Analyse how sentiment has changed over time (03-Nov-23 - 09-Nov-23); 9: Analyse how sentiment has changed over time (03-Nov-23 - 09-Nov-23)
Visualise the sentiment trends | 03-Nov-2023 | 09-Nov-2023 | 3: Visualise the sentiment trends (03-Nov-23 - 09-Nov-23); 4: Visualise the sentiment trends (03-Nov-23 - 09-Nov-23); 5: Visualise the sentiment trends (03-Nov-23 - 09-Nov-23); 6: Visualise the sentiment trends (03-Nov-23 - 09-Nov-23); 7: Visualise the sentiment trends (03-Nov-23 - 09-Nov-23); 8: Visualise the sentiment trends (03-Nov-23 - 09-Nov-23); 9: Visualise the sentiment trends (03-Nov-23 - 09-Nov-23)
Looking for Correlations | 03-Nov-2023 | 09-Nov-2023 | 3: Looking for Correlations (03-Nov-23 - 09-Nov-23); 4: Looking for Correlations (03-Nov-23 - 09-Nov-23); 5: Looking for Correlations (03-Nov-23 - 09-Nov-23); 6: Looking for Correlations (03-Nov-23 - 09-Nov-23); 7: Looking for Correlations (03-Nov-23 - 09-Nov-23); 8: Looking for Correlations (03-Nov-23 - 09-Nov-23); 9: Looking for Correlations (03-Nov-23 - 09-Nov-23)
Investigate the correlation between sentiment and key events | 03-Nov-2023 | 09-Nov-2023 | 3: Investigate the correlation between sentiment and key events (03-Nov-23 - 09-Nov-23); 4: Investigate the correlation between sentiment and key events (03-Nov-23 - 09-Nov-23); 5: Investigate the correlation between sentiment and key events (03-Nov-23 - 09-Nov-23); 6: Investigate the correlation between sentiment and key events (03-Nov-23 - 09-Nov-23); 7: Investigate the correlation between sentiment and key events (03-Nov-23 - 09-Nov-23); 8: Investigate the correlation between sentiment and key events (03-Nov-23 - 09-Nov-23); 9: Investigate the correlation between sentiment and key events (03-Nov-23 - 09-Nov-23)
Analyse correlations with economic indicators | 03-Nov-2023 | 13-Nov-2023 | 3: Analyse correlations with economic indicators (03-Nov-23 - 13-Nov-23); 4: Analyse correlations with economic indicators (03-Nov-23 - 13-Nov-23); 5: Analyse correlations with economic indicators (03-Nov-23 - 13-Nov-23); 6: Analyse correlations with economic indicators (03-Nov-23 - 13-Nov-23); 7: Analyse correlations with economic indicators (03-Nov-23 - 13-Nov-23); 8: Analyse correlations with economic indicators (03-Nov-23 - 13-Nov-23); 9: Analyse correlations with economic indicators (03-Nov-23 - 13-Nov-23); 10: Analyse correlations with economic indicators (03-Nov-23 - 13-Nov-23); 11: Analyse correlations with economic indicators (03-Nov-23 - 13-Nov-23); 12: Analyse correlations with economic indicators (03-Nov-23 - 13-Nov-23); 13: Analyse correlations with economic indicators (03-Nov-23 - 13-Nov-23)
Properly create, develop and train a model | 03-Nov-2023 | 13-Nov-2023 | 3: Properly create, develop and train a model (03-Nov-23 - 13-Nov-23); 4: Properly create, develop and train a model (03-Nov-23 - 13-Nov-23); 5: Properly create, develop and train a model (03-Nov-23 - 13-Nov-23); 6: Properly create, develop and train a model (03-Nov-23 - 13-Nov-23); 7: Properly create, develop and train a model (03-Nov-23 - 13-Nov-23); 8: Properly create, develop and train a model (03-Nov-23 - 13-Nov-23); 9: Properly create, develop and train a model (03-Nov-23 - 13-Nov-23); 10: Properly create, develop and train a model (03-Nov-23 - 13-Nov-23); 11: Properly create, develop and train a model (03-Nov-23 - 13-Nov-23); 12: Properly create, develop and train a model (03-Nov-23 - 13-Nov-23); 13: Properly create, develop and train a model (03-Nov-23 - 13-Nov-23)
Considering LLM - Exploring | 03-Nov-2023 | 13-Nov-2023 | 3: Considering LLM - Exploring (03-Nov-23 - 13-Nov-23); 4: Considering LLM - Exploring (03-Nov-23 - 13-Nov-23); 5: Considering LLM - Exploring (03-Nov-23 - 13-Nov-23); 6: Considering LLM - Exploring (03-Nov-23 - 13-Nov-23); 7: Considering LLM - Exploring (03-Nov-23 - 13-Nov-23); 8: Considering LLM - Exploring (03-Nov-23 - 13-Nov-23); 9: Considering LLM - Exploring (03-Nov-23 - 13-Nov-23); 10: Considering LLM - Exploring (03-Nov-23 - 13-Nov-23); 11: Considering LLM - Exploring (03-Nov-23 - 13-Nov-23); 12: Considering LLM - Exploring (03-Nov-23 - 13-Nov-23); 13: Considering LLM - Exploring (03-Nov-23 - 13-Nov-23)
Monitoring and Control - Results and Conclusions |  |  | 16: Monitoring and Control - Results and Conclusions
Reviewing of insights and findings so far | 13-Nov-2023 | 20-Nov-2023 | 13: Reviewing of insights and findings so far (13-Nov-23 - 20-Nov-23); 14: Reviewing of insights and findings so far (13-Nov-23 - 20-Nov-23); 15: Reviewing of insights and findings so far (13-Nov-23 - 20-Nov-23); 16: Reviewing of insights and findings so far (13-Nov-23 - 20-Nov-23); 17: Reviewing of insights and findings so far (13-Nov-23 - 20-Nov-23); 18: Reviewing of insights and findings so far (13-Nov-23 - 20-Nov-23); 19: Reviewing of insights and findings so far (13-Nov-23 - 20-Nov-23); 20: Reviewing of insights and findings so far (13-Nov-23 - 20-Nov-23)
Reasoning and Explanations | 13-Nov-2023 | 20-Nov-2023 | 13: Reasoning and Explanations (13-Nov-23 - 20-Nov-23); 14: Reasoning and Explanations (13-Nov-23 - 20-Nov-23); 15: Reasoning and Explanations (13-Nov-23 - 20-Nov-23); 16: Reasoning and Explanations (13-Nov-23 - 20-Nov-23); 17: Reasoning and Explanations (13-Nov-23 - 20-Nov-23); 18: Reasoning and Explanations (13-Nov-23 - 20-Nov-23); 19: Reasoning and Explanations (13-Nov-23 - 20-Nov-23); 20: Reasoning and Explanations (13-Nov-23 - 20-Nov-23)
Answering the questions | 13-Nov-2023 | 20-Nov-2023 | 13: Answering the questions (13-Nov-23 - 20-Nov-23); 14: Answering the questions (13-Nov-23 - 20-Nov-23); 15: Answering the questions (13-Nov-23 - 20-Nov-23); 16: Answering the questions (13-Nov-23 - 20-Nov-23); 17: Answering the questions (13-Nov-23 - 20-Nov-23); 18: Answering the questions (13-Nov-23 - 20-Nov-23); 19: Answering the questions (13-Nov-23 - 20-Nov-23); 20: Answering the questions (13-Nov-23 - 20-Nov-23)
Monitoring and Control - Updating BoE with plan & recomendations |  |  | 16: Monitoring and Control - Updating BoE with plan & recomendations
Reviewing of insights, findings & visualisations so far | 13-Nov-2023 | 20-Nov-2023 | 13: Reviewing of insights, findings & visualisations so far (13-Nov-23 - 20-Nov-23); 14: Reviewing of insights, findings & visualisations so far (13-Nov-23 - 20-Nov-23); 15: Reviewing of insights, findings & visualisations so far (13-Nov-23 - 20-Nov-23); 16: Reviewing of insights, findings & visualisations so far (13-Nov-23 - 20-Nov-23); 17: Reviewing of insights, findings & visualisations so far (13-Nov-23 - 20-Nov-23); 18: Reviewing of insights, findings & visualisations so far (13-Nov-23 - 20-Nov-23); 19: Reviewing of insights, findings & visualisations so far (13-Nov-23 - 20-Nov-23); 20: Reviewing of insights, findings & visualisations so far (13-Nov-23 - 20-Nov-23)
Updating BOE with plan | 13-Nov-2023 | 20-Nov-2023 | 13: Updating BOE with plan (13-Nov-23 - 20-Nov-23); 14: Updating BOE with plan (13-Nov-23 - 20-Nov-23); 15: Updating BOE with plan (13-Nov-23 - 20-Nov-23); 16: Updating BOE with plan (13-Nov-23 - 20-Nov-23); 17: Updating BOE with plan (13-Nov-23 - 20-Nov-23); 18: Updating BOE with plan (13-Nov-23 - 20-Nov-23); 19: Updating BOE with plan (13-Nov-23 - 20-Nov-23); 20: Updating BOE with plan (13-Nov-23 - 20-Nov-23)
Reasoning and Explanations | 13-Nov-2023 | 20-Nov-2023 | 13: Reasoning and Explanations (13-Nov-23 - 20-Nov-23); 14: Reasoning and Explanations (13-Nov-23 - 20-Nov-23); 15: Reasoning and Explanations (13-Nov-23 - 20-Nov-23); 16: Reasoning and Explanations (13-Nov-23 - 20-Nov-23); 17: Reasoning and Explanations (13-Nov-23 - 20-Nov-23); 18: Reasoning and Explanations (13-Nov-23 - 20-Nov-23); 19: Reasoning and Explanations (13-Nov-23 - 20-Nov-23); 20: Reasoning and Explanations (13-Nov-23 - 20-Nov-23)
Create a presentation | 13-Nov-2023 | 20-Nov-2023 | 13: Create a presentation (13-Nov-23 - 20-Nov-23); 14: Create a presentation (13-Nov-23 - 20-Nov-23); 15: Create a presentation (13-Nov-23 - 20-Nov-23); 16: Create a presentation (13-Nov-23 - 20-Nov-23); 17: Create a presentation (13-Nov-23 - 20-Nov-23); 18: Create a presentation (13-Nov-23 - 20-Nov-23); 19: Create a presentation (13-Nov-23 - 20-Nov-23); 20: Create a presentation (13-Nov-23 - 20-Nov-23)
Assignment 2: Initial recommendation pitch - 20% |  |  | 16: Assignment 2: Initial recommendation pitch - 20%
Presentation | 20-Nov-2023 | 20-Nov-2023 | 20: Presentation (20-Nov-23 - 20-Nov-23)
Phase 3 of Analysis Monitoring and Control - Reporting and Presentation |  |  | 16: Phase 3 of Analysis Monitoring and Control - Reporting and Presentation
Making changes following feedback from BoE from intial recomendations pitch | 13-Nov-2023 | 27-Nov-2023 | 13: Making changes following feedback from BoE from intial recomendations pitch (13-Nov-23 - 27-Nov-23); 14: Making changes following feedback from BoE from intial recomendations pitch (13-Nov-23 - 27-Nov-23); 15: Making changes following feedback from BoE from intial recomendations pitch (13-Nov-23 - 27-Nov-23); 16: Making changes following feedback from BoE from intial recomendations pitch (13-Nov-23 - 27-Nov-23); 17: Making changes following feedback from BoE from intial recomendations pitch (13-Nov-23 - 27-Nov-23); 18: Making changes following feedback from BoE from intial recomendations pitch (13-Nov-23 - 27-Nov-23); 19: Making changes following feedback from BoE from intial recomendations pitch (13-Nov-23 - 27-Nov-23); 20: Making changes following feedback from BoE from intial recomendations pitch (13-Nov-23 - 27-Nov-23); 21: Making changes following feedback from BoE from intial recomendations pitch (13-Nov-23 - 27-Nov-23); 22: Making changes following feedback from BoE from intial recomendations pitch (13-Nov-23 - 27-Nov-23); 23: Making changes following feedback from BoE from intial recomendations pitch (13-Nov-23 - 27-Nov-23); 24: Making changes following feedback from BoE from intial recomendations pitch (13-Nov-23 - 27-Nov-23); 25: Making changes following feedback from BoE from intial recomendations pitch (13-Nov-23 - 27-Nov-23); 26: Making changes following feedback from BoE from intial recomendations pitch (13-Nov-23 - 27-Nov-23); 27: Making changes following feedback from BoE from intial recomendations pitch (13-Nov-23 - 27-Nov-23)
Reviewing of insights, findings & visualisations again - Can we improve? | 13-Nov-2023 | 27-Nov-2023 | 13: Reviewing of insights, findings & visualisations again - Can we improve? (13-Nov-23 - 27-Nov-23); 14: Reviewing of insights, findings & visualisations again - Can we improve? (13-Nov-23 - 27-Nov-23); 15: Reviewing of insights, findings & visualisations again - Can we improve? (13-Nov-23 - 27-Nov-23); 16: Reviewing of insights, findings & visualisations again - Can we improve? (13-Nov-23 - 27-Nov-23); 17: Reviewing of insights, findings & visualisations again - Can we improve? (13-Nov-23 - 27-Nov-23); 18: Reviewing of insights, findings & visualisations again - Can we improve? (13-Nov-23 - 27-Nov-23); 19: Reviewing of insights, findings & visualisations again - Can we improve? (13-Nov-23 - 27-Nov-23); 20: Reviewing of insights, findings & visualisations again - Can we improve? (13-Nov-23 - 27-Nov-23); 21: Reviewing of insights, findings & visualisations again - Can we improve? (13-Nov-23 - 27-Nov-23); 22: Reviewing of insights, findings & visualisations again - Can we improve? (13-Nov-23 - 27-Nov-23); 23: Reviewing of insights, findings & visualisations again - Can we improve? (13-Nov-23 - 27-Nov-23); 24: Reviewing of insights, findings & visualisations again - Can we improve? (13-Nov-23 - 27-Nov-23); 25: Reviewing of insights, findings & visualisations again - Can we improve? (13-Nov-23 - 27-Nov-23); 26: Reviewing of insights, findings & visualisations again - Can we improve? (13-Nov-23 - 27-Nov-23); 27: Reviewing of insights, findings & visualisations again - Can we improve? (13-Nov-23 - 27-Nov-23)
Report Writing | 13-Nov-2023 | 27-Nov-2023 | 13: Report Writing (13-Nov-23 - 27-Nov-23); 14: Report Writing (13-Nov-23 - 27-Nov-23); 15: Report Writing (13-Nov-23 - 27-Nov-23); 16: Report Writing (13-Nov-23 - 27-Nov-23); 17: Report Writing (13-Nov-23 - 27-Nov-23); 18: Report Writing (13-Nov-23 - 27-Nov-23); 19: Report Writing (13-Nov-23 - 27-Nov-23); 20: Report Writing (13-Nov-23 - 27-Nov-23); 21: Report Writing (13-Nov-23 - 27-Nov-23); 22: Report Writing (13-Nov-23 - 27-Nov-23); 23: Report Writing (13-Nov-23 - 27-Nov-23); 24: Report Writing (13-Nov-23 - 27-Nov-23); 25: Report Writing (13-Nov-23 - 27-Nov-23); 26: Report Writing (13-Nov-23 - 27-Nov-23); 27: Report Writing (13-Nov-23 - 27-Nov-23)
Create final presentation | 13-Nov-2023 | 27-Nov-2023 | 13: Create final presentation (13-Nov-23 - 27-Nov-23); 14: Create final presentation (13-Nov-23 - 27-Nov-23); 15: Create final presentation (13-Nov-23 - 27-Nov-23); 16: Create final presentation (13-Nov-23 - 27-Nov-23); 17: Create final presentation (13-Nov-23 - 27-Nov-23); 18: Create final presentation (13-Nov-23 - 27-Nov-23); 19: Create final presentation (13-Nov-23 - 27-Nov-23); 20: Create final presentation (13-Nov-23 - 27-Nov-23); 21: Create final presentation (13-Nov-23 - 27-Nov-23); 22: Create final presentation (13-Nov-23 - 27-Nov-23); 23: Create final presentation (13-Nov-23 - 27-Nov-23); 24: Create final presentation (13-Nov-23 - 27-Nov-23); 25: Create final presentation (13-Nov-23 - 27-Nov-23); 26: Create final presentation (13-Nov-23 - 27-Nov-23); 27: Create final presentation (13-Nov-23 - 27-Nov-23)
Review Code | 13-Nov-2023 | 27-Nov-2023 | 13: Review Code (13-Nov-23 - 27-Nov-23); 14: Review Code (13-Nov-23 - 27-Nov-23); 15: Review Code (13-Nov-23 - 27-Nov-23); 16: Review Code (13-Nov-23 - 27-Nov-23); 17: Review Code (13-Nov-23 - 27-Nov-23); 18: Review Code (13-Nov-23 - 27-Nov-23); 19: Review Code (13-Nov-23 - 27-Nov-23); 20: Review Code (13-Nov-23 - 27-Nov-23); 21: Review Code (13-Nov-23 - 27-Nov-23); 22: Review Code (13-Nov-23 - 27-Nov-23); 23: Review Code (13-Nov-23 - 27-Nov-23); 24: Review Code (13-Nov-23 - 27-Nov-23); 25: Review Code (13-Nov-23 - 27-Nov-23); 26: Review Code (13-Nov-23 - 27-Nov-23); 27: Review Code (13-Nov-23 - 27-Nov-23)
Closure - Final Review and Submission |  |  | 16: Closure - Final Review and Submission
Review the report and presentation for completeness and accuracy | 20-Nov-2023 | 27-Nov-2023 | 20: Review the report and presentation for completeness and accuracy (20-Nov-23 - 27-Nov-23); 21: Review the report and presentation for completeness and accuracy (20-Nov-23 - 27-Nov-23); 22: Review the report and presentation for completeness and accuracy (20-Nov-23 - 27-Nov-23); 23: Review the report and presentation for completeness and accuracy (20-Nov-23 - 27-Nov-23); 24: Review the report and presentation for completeness and accuracy (20-Nov-23 - 27-Nov-23); 25: Review the report and presentation for completeness and accuracy (20-Nov-23 - 27-Nov-23); 26: Review the report and presentation for completeness and accuracy (20-Nov-23 - 27-Nov-23); 27: Review the report and presentation for completeness and accuracy (20-Nov-23 - 27-Nov-23)
Gather final feedback from tea | 20-Nov-2023 | 27-Nov-2023 | 20: Gather final feedback from tea (20-Nov-23 - 27-Nov-23); 21: Gather final feedback from tea (20-Nov-23 - 27-Nov-23); 22: Gather final feedback from tea (20-Nov-23 - 27-Nov-23); 23: Gather final feedback from tea (20-Nov-23 - 27-Nov-23); 24: Gather final feedback from tea (20-Nov-23 - 27-Nov-23); 25: Gather final feedback from tea (20-Nov-23 - 27-Nov-23); 26: Gather final feedback from tea (20-Nov-23 - 27-Nov-23); 27: Gather final feedback from tea (20-Nov-23 - 27-Nov-23)
Submit the report to the Bank of England's Data Strategy & Implementation Division | 20-Nov-2023 | 27-Nov-2023 | 20: Submit the report to the Bank of England's Data Strategy & Implementation Division (20-Nov-23 - 27-Nov-23); 21: Submit the report to the Bank of England's Data Strategy & Implementation Division (20-Nov-23 - 27-Nov-23); 22: Submit the report to the Bank of England's Data Strategy & Implementation Division (20-Nov-23 - 27-Nov-23); 23: Submit the report to the Bank of England's Data Strategy & Implementation Division (20-Nov-23 - 27-Nov-23); 24: Submit the report to the Bank of England's Data Strategy & Implementation Division (20-Nov-23 - 27-Nov-23); 25: Submit the report to the Bank of England's Data Strategy & Implementation Division (20-Nov-23 - 27-Nov-23); 26: Submit the report to the Bank of England's Data Strategy & Implementation Division (20-Nov-23 - 27-Nov-23); 27: Submit the report to the Bank of England's Data Strategy & Implementation Division (20-Nov-23 - 27-Nov-23)
Live Presentation (Scheduled by the Bank of England) | 27-Nov-2023 | 27-Nov-2023 | 27: Live Presentation (Scheduled by the Bank of England) (27-Nov-23 - 27-Nov-23)
Assignment 3: Final report and presentation - 50% |  |  | 16: Assignment 3: Final report and presentation - 50%
PDF report | 27-Nov-2023 | 27-Nov-2023 | 27: PDF report (27-Nov-23 - 27-Nov-23)
Code Submission | 27-Nov-2023 | 27-Nov-2023 | 27: Code Submission (27-Nov-23 - 27-Nov-23)
Presentation | 27-Nov-2023 | 27-Nov-2023 | 27: Presentation (27-Nov-23 - 27-Nov-23)
Assignment 4: Individual reflection -15% |  |  | 16: Assignment 4: Individual reflection -15%
PDF document - 500 Words | 27-Nov-2023 | 27-Nov-2023 | 27: PDF document - 500 Words (27-Nov-23 - 27-Nov-23)